## Product Backlog
Planned Sprint | Planned Sprint | Planned Sprint | Planned Sprint | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US001 | As a data engineer, I want to collect the data , so that it can be used for model training. | MUST HAVE | Dataset availability | Data Science team | Completed
Sprint 2 | Sprint 2 | US002 | As a data engineer, I want to perform data preprocessing. | MUST HAVE | Cleaned data | Data Science team | Completed
Sprint 3 | Sprint 3 | US003 | As a data scientist, I want to train an AI model for the detection of traffic and status of people with helmet and without helmet. | MUST HAVE | Trained model | AI-ML team | Completed
Sprint 4 | Sprint 4 | US004 | As a frontend developer, I want to create an user-interface using streamlit. | MUST HAVE | API is ready | Frontend team | Completed
Sprint 5 | Sprint 5 | US005 | As a Web developer, I want to create an user interfaceser-interface using Flask. | SHOULD HAVE | Frontend and Backend integration | Frontend and Backend team | Completed
.
Note on F1: ====== ID#AAABwKRy8m0 Sumeet Kumar Barua08 (2025-11-16 13:05:16) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: ====== ID#AAABwKRy8mk Please enter the dates in either of these formats (2025-11-16 13:05:16) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABwKPojxM Please enter the dates in either of these formats (2025-11-16 13:05:16) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABwKRy8mU Sumeet Kumar Barua08 (2025-11-16 13:05:16) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABwKRy8mc Sumeet Kumar Barua08 (2025-11-16 13:05:16) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABwKRy8mQ Sumeet Kumar Barua08 (2025-11-16 13:05:16) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABwKRy8nE Sumeet Kumar Barua08 (2025-11-16 13:05:16) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABwKRy8mM Sumeet Kumar Barua08 (2025-11-16 13:05:16) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABwKRy8nI Sumeet Kumar Barua08 (2025-11-16 13:05:16) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABwKRy8nA Sumeet Kumar Barua08 (2025-11-16 13:05:16) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABwKRy8ms Sumeet Kumar Barua08 (2025-11-16 13:05:16) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABwKRy8m4 Sumeet Kumar Barua08 (2025-11-16 13:05:16) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABwKRy8m8 Sumeet Kumar Barua08 (2025-11-16 13:05:16) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABwKRy8mw Sumeet Kumar Barua08 (2025-11-16 13:05:16) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABwKRy8mY Sumeet Kumar Barua08 (2025-11-16 13:05:16) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABwKRy8nM Sumeet Kumar Barua08 (2025-11-16 13:05:16) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABwKRy8mo Sumeet Kumar Barua08 (2025-11-16 13:05:16) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABwKRy8mg Sumeet Kumar Barua08 (2025-11-16 13:05:16) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7